## Features
FindFiles
Feature | Status | Description
General
Main Window | y
menu | y
file | y
search locations | n
preferences | n
quit | y
edit | y
copy | y
view | y
detail panel below | y
window | y
new window | y
help | y
check for update | n
contact customer support | n
license | n
open source licenses | n
about | n
toolbar | y
source selector | y
search field | y
pulldown with recent searches | n
search button | n
results table | y
columns
file | y
path | y
size | y
last modified | y
placeholder shows search expression or no content in table message | y
popup menu | n
detail pane | y
shows selected file | y
quick navigation on the left | y
shows line | y
text area | y
with highlights | y
popup menu | n
status line | y
copyright | y
on click navigates to Help->About | n
shows searching expression or number of files found | y
remember settings | y
window position | y
Search
fast byte-oriented search with multiple patterns | n
includes file names | n
Sources Dialog | n
locations table | n
add folder | n
remove folder | n
edit folder | n
filters | n
include files | n
include folders | n
exclude files | n
exclude folders | n
ignore system files | n
ignore hidden files | n
Save button | n
Cancel Button | n
Options | n
color themes | n
dark | n
light | n
format options | n
Check for Updates Dialog | n
checking | n
result | n
web site | n
License Dialog | n
license | n
Copy to Clipboard button | n
OK | n
Open Source Licenses Dialog | n
licenses table | n
license | n
Copy to Clipboard button | n
OK | n
About Dialog | n
logo | n
link | n
Features implemented: | 31
To be implemented: | 49
To be determined: | 0
Total: | 80
| Percent complete: | 38.75%

## Progress
FindFiles
Date | Done | To Do | To Be Defined | Defects | Version | %
2017-04-12 | 0 | 0 | 0 | 0 | Start | 0%
2017-06-04 | 28 | 50 | 0 | 0 | 0.00.7 | 35.9%
2017-07-22 | 31 | 49 | 0 | 0 | 0.00.8 | 38.75%
Total | Done | To Do | To Be Defined | Defects | Version | 38.75%
80 | 31 | 49 | 0 | 0
ETA: | 2017-12-28 15:29
2017-10-03